## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Group C | Completed | 20
Project title | Student Accommodation Payment & Management System Prototype | In Progress | 2
Stakeholder or organisation | Gladys Belle : owner/manager of 3 student accommodation properties | Not Started | 0
Group mentor |  | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period |  | Overdue | 0
Overall status | Not Started
Overall % complete | 92.39% | Contribution Summary | Count
Main achievement |  | Contribution entries | 0
Main challenge |  | Verified entries | 0
Next planned activity |  | Unverified entries | 0
|  | Stakeholder engagements | 2

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | FB Amatebelle | 2026-08-18 | 2026-08-21 | Completed | 100 | SRS Document | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Seleke TM | 2026-08-23 | 2026-08-24 | Completed | 100 | SRS Document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Seleke TM | 2026-08-23 | 2026-08-24 | Completed | 100 | SRS Document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Mohapi MA | 2026-08-22 | 2026-09-22 | Completed | 100 | Interview questions document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | FB Amatebelle & Seleke TM | 2026-08-23 | 2026-08-23 | Completed | 100 | Interview Notes | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | FB Amatebelle & Mohapi MA | 2026-08-25 | 2026-08-25 | Completed | 100 | SRS Document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Seleke TM | 2026-08-26 | 2026-08-26 | Completed | 100 |  | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Tshitangano TD | 2026-08-24 | 2026-08-24 | Completed | 100 | Github repository link | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Tshitangano TD | 2026-08-24 | 2026-08-24 | Completed | 100 | SupaBase URL | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record |  |  |  | In Progress | 50 |  | Yes |  | On Track
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection |  |  |  | Completed | 100 | This Document | Yes |  | Completed
U2-01 | Unit 2/ Phase 1 | Activity 2.1 | Conduct a Feasibility Study | FB Amatebelle & Molelekeng KP | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-02 | Unit 2/ Phase 1 | Activity 2.1 | Technical feasibility | FB Amatebelle | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-03 | Unit 2/ Phase 1 | Activity 2.1 | Operational feasibility | Molelekeng KP | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-04 | Unit 2/ Phase 1 | Activity 2.1 | economical feasibility | Molelekeng KP | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-05 | Unit 2/ Phase 1 | Activity 2.1 | Schedule feasibility | Molelekeng KP | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-06 | Unit 2/ Phase 1 | Activity 2.1 | Legal feasibility | FB Amatebelle | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-07 | Unit 2/ Phase 1 | Activity 2.1 | Ethical feasibility | Molelekeng KP | 2026-08-31 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-08 | Unit 2/ Phase 1 | Activity 2.1 | Feasibility conclusion | All Members | 2026-09-01 | 2026-09-01 | Completed | 100 | Feasibility Document | Yes |  | Completed
U2-09 | Unit 2/ Phase 1 | Activity 2.2 | Risk Register | Gongxeka IQ | 2026-08-26 | 2026-08-28 | Completed | 100 | Risk Register document | Yes |  | Completed
U2-10 | Unit 2/ Phase 1 | Activity 2.3 | Refine the SRS | Mohapi MA | 2026-10-02 | 2026-10-02 | Completed | 100 | SRS Document | Yes |  | Completed
U2-11 | Unit 2/ Phase 1 | Activity 2.3 | Refine the Project Plan | FB Amatebelle & Gongxeka IQ | 2026-09-03 | 2026-09-04 | In Progress | 75 | This Document | Yes |  | On Track
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Fidelis | 223040545 | Unit 1 / Phase 1 | 1.3 |  | Compile the initial SRS
Fidelis | 223040545 | Unit 1 / Phase 1 | 1.2 |  | Conducted the stakeholder interview
MA Mohapi | 222070281 | Unit 1 / Phase 1 | 1.2 |  | Prepare stakeholder interview questions
TM Seleke | 223044798 | Unit 1 / Phase 1 | 1.1 |  | Document the current process and problem
TM Seleke | 223044798 | Unit 1 / Phase 1 | 1.1 |  | Define the project aim, objectives and scope
Fidelis | 223040545 | Unit 1 / Phase 1 | 1.3 |  | Create the initial Microsoft Project schedule
TD Tshitangano | 223022577 | Unit 1 / Phase 1 | 1.3 |  | Create and configure the GitHub repository
TD Tshitangano | 223022577 | Unit 1 / Phase 1 | 1.3 |  | Create the initial Supabase project

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
2026-08-24 | Unit 1 / Phase 1 | Online Meeting | Stakeholder Interview | All Members | present | Full needs assessment covering payments, maintenance, security and access ,see Stakeholder Interview Notes |  | Interview notes Document
2026-08-27 | Unit 1 / Phase 1 | Email | Confirmation Findings | FB Amatebelle | present | Confirmation of interview summary findings |  | Confirmation of findings document

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
23/08/2026 | Unit 1 / Phase 1 | Inactive participation to group meetings | Slower task completion due to unavailability | Issued a warning in a public space that if the issue is not resolved, measures will be taken with the lecturer | Leeuw GA | 2026-08-23 | Resolved
25/08/2026 | Unit 1 / Phase 1 | Not yet confident using Microsoft Project | Risk of an incomplete/inaccurate schedule | Used a structured task-list template and step-by-step guidance to build the schedule | Amatebelle FB & Seleke TM | 2026-08-25 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 18 August 2026 - 4 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | No
What was completed during this phase? | The initial SRS document, draft of stakeholder questions and interview, Defining the project aim, objectives and scope , Microsoft Project Schedule, creation of the GitHub repository and Supabase ,documentation of the current process and problem. | Stakeholder engagement recorded | Yes
What remains incomplete? | Group evaluation report | Challenges and actions updated | Yes
Why is it incomplete? | The group is struggling to agree on an approach on how the evaluation report can be conducted. Lack of engagement has caused a delay, affecting our ability to finish phase 1 on time. | Group reflection completed | Yes
Which contributions were particularly important? | The stakeholder's contribution was crucial, as it gave us clear direction and helped us identify key issues that we, as a team could address to the best of our ability. The most important contribution was teamwork. Although we had a rough start with members arriving late or not showing up, we eventually found common ground and found ways to work together to complete this phase. | Microsoft Project updated | Yes
Were there participation concerns? | One member was initially inactive in group meetings; this was raised with the group and resolved after a direct conversation, recorded in the Challenges & Actions log. No other participation concerns were identified. | GitHub evidence available | Yes
What will the group improve in the next phase? | Improved team communication, meetings scheduled in time with agreement from all members on the proposed dates and times, and supporting one another when facing challenges with assigned tasks. | Confidential peer check completed | No
Main priority for the next phase | Each team member should have a clear understanding of what is required for the next phase, with tasks divided equally and assigned on time so that we have enough time to support any issues that might happen. We also should take note of the risk register to anticipate potential challenges and how to tackle them, ensuring that we complete the phase on time.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Student Accomodation and Management System | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | We must use the allocated time wisely, as working last minute leads to rushed and poor quality work. Each member should stick to the given schedule. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | The first stakeholder interview. Miss Glady clearly stated the challenges she faces in her business and was very easy to work with, answering all our questions to the best of her ability. The meeting was a great success, with full participation from all our team members. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Coordinating the Microsoft Project schedule was difficult, as most of the group had limited prior experience with the tool. This slowed down the scheduling task and required extra time to learn dependencies, summary tasks and milestones correctly. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | A project manager/ group leader was assigned at the beginning of the project. We reviewed the activities that were provided across both units and considered each member's strengths and confidence towards which activity, allowing everyone to choose the tasks they were most comfortable with doing.
Did all members contribute fairly? Explain. | At the beginning we had an issue with a group member who consistently missed group meetings but it has been resolved. Apart from that, attendance has been consistent, and all the members have completed their assigned tasks within the given time frame.
How did the group handle disagreements or delays? | We spoke about it as a team and decided that the group leader must address the issue on our WhatsApp group so that each person is well aware of what happened and the consequences, if the matter would happen again. When there was a delay, available team members were asked to help out to increase the progress the specific task.
What did the group learn from the stakeholder? | We learned that managing a student accomodation without a proper system can lead to significant losses and exhaustion. She mentioned that she is not the only one facing this challenge, as many landlords are sceptical about technology and continue to use manual methods, which are no longer effective given the growing number of students and the amount of information that must be captured at the end of each month which is a very tiring process. Implementing a system will not only benefit her business but will also improve her well-being allowing her to clearly track how her business is doing.
Improvement action 1 for the next phase | Update the progress tracker continuously throughout each phase rather than mainly at the end, to reduce last-minute compilation work.
Improvement action 2 for the next phase | Build in dedicated early learning time for tools the group is less confident with (Microsoft Project, Supabase, OTP authentication in ASP.NET) before they are needed for a deliverable.
Priority for the next phase | Each team member should have a clear understanding of what is required for the next phase, with tasks divided equally and assigned on time so that we have enough time to support any issues that might happen. We also should take note of the risk register to anticipate potential challenges and how to tackle them, ensuring that we complete the phase on time.